## Project Plan
Phase | Activity | Start Date | End Date | Resource
Scope & Requirements | Access current Crime visualiztion offerings | 2019-09-09 | 2019-09-14 | Team
| Finalize Users of End Product | 2019-09-12 | 2019-09-15 | Team
| Envision and Document End User Wishlist | 2019-09-16 | 09/20/219 | Team
| Finalize an End sate Product features | 2019-09-17 | 2019-09-20 | Team
| Determine Global Vs National Crimes Scope | 2019-09-23 | 2019-09-25 | Team
| Finalize the Crime Types & Intensity of Crimes under Scope | 2019-09-23 | 2019-09-25 | Team
| Gap Analysis & Finalization of User Stories with KPIs | 2019-09-23 | 2019-09-25 | Team
| Create Budgetary Effort and Cost | 2019-09-26 | 2019-10-04 | Team
| Proposal Document | 2019-10-11 | 2019-10-11 | atharp6, sraj, sedwards72
| Proposal Presentation | 2019-10-11 | 2019-10-11 | sgupta679, rodowd3, nhussain
Planning & Estimation | Narrow Down on Data Sources | 2019-09-26 | 2019-10-04 | Team
| Evaluate Software Req | 2019-10-02 | 2019-10-06 | Team
| Evaluate Sentiment Analysis Techniiques | 2019-10-06 | 2019-10-16 | Team
| Evaluate Model Requirements | 2019-10-06 | 2019-10-16 | Team
| Finalize Technology Stack | 2019-10-06 | 2019-10-16 | Team
| Evaluate & Finalize Infrastrastructure Req including Hosting Providers | 2019-10-02 | 2019-10-18 | Team
| Finalize High Level Design & Create Mockups | 2019-10-10 | 2019-10-20 | Team
| Finalize Code Development, Versioning , Control and Deployment Procedures | 2019-10-10 | 2019-10-20 | Team
| Re-visit Effort and Cost | 2019-10-20 | 2019-10-22 | Team
Environment Setup | Chosse Servers as per sizing reqms | 2019-10-21 | 2019-10-22
| Choose the VDI Image to be used during spinning of servers | 2019-10-21 | 2019-10-22
| Configure the Access Set up | 2019-10-21 | 2019-10-22
| Set up Auto Scaling | 2019-10-21 | 2019-10-22
| Open the firewalls and Open ports as per requirement | 2019-10-22 | 2019-10-23
| Create Twitter API account and Genreate the API Keys and Tokens | 2019-10-22 | 2019-10-23
Application Control | Creation of Shell Script to Start and Stop Data Streaming Application | 2019-10-23 | 2019-10-25 |  | Collecting Twitter Data using API with Tweepy, MYSQL and Python
Data Streaming , Pre-Processing of Twitter Data | Creation of Scala Script to Perform data cleaning using Spark job | 2019-10-23 | 2019-11-02
Feature extraction , Sentiment Analysis and classification | Creation of Scala Script to Perform Feature extraction , Sentiment analysis and classification using Spark Job | 2019-10-25 | 2019-11-08 |  | Create Tweepy Stream Listener for receiving Tweets
| Configure and Monitor the Dara Feed using Kylo App | 2019-10-28 | 11/31/2019 |  | Create MYSQL tables Table to store Tweets from Stream Listener
Data Storage and archival | Deign Storaghe for storage and determine the archival strategy | 2019-10-23 | 2019-10-31
Visualization | Creation of Choloropeth Map | 2019-11-02 | 2019-11-05
| Feeding of processed streaming data and create transitions in the map with a delay | 2019-11-05 | 2019-11-16
Web Application | Create a iframe inWebsite to display the real time Heatmap transition and the Feeds from twitter | 2019-11-01 | 2019-11-20
End to End Integration & Testing | Intgerate and perform E2E testing from data collection ,theu real time visualization from a functionality standpoint | 2019-11-21 | 2019-11-28
| Check the performance of each component | 2019-11-23 | 2019-11-28
| Validate whether the auto sclaing in the Infratsructure side is working as appropriate | 2019-11-23 | 2019-11-28
Monitoring & Analysis | Monitor the Drift in Data | 2019-11-28 | 2019-11-30
| Monitor the Model Drift and make necessary changes in the algorithm | 2019-11-28 | 2019-11-30
| Monitor the application performance | 2019-11-28 | 2019-11-30
| Monitor the Webiste Hit Analytics and any system exceptions | 2019-11-28 | 2019-11-30
Launch , Project Presentation & Looking Forward | Document the Project Current state, Improvements to be made, scaling and Roll Out details | 2019-11-30 | 2019-11-30
| Gather Feedback from End Users | 2019-11-30 | 2019-12-03
| Final Presentation of the Mean Viable product | 2019-12-03 | 2019-12-03